## RFC Form
Request for Change Form (RFC) | [7 empty] | RFC Number: |  | RFC-DX-2023-001
[8 empty] | Revision Number: |  | 0
• INITIATION -- To be accomplished by the I.T. Change INITIATOR
Initiator's Name: | Mary Jane S. Ballon |  |  |  |  | Date Requested: |  | October 9, 2023
Project Title: | New VPE System |  |  |  |  | Target Implementation Date: |  |  | 2024-02-28
Reason for Change / Brief Description: | This change request for VPE System (Server CPH64) is due to the following reasons: 1) Operating System (Windows Server 2012) is End-of-Life (EOL) in October 2023; 2) CPH64 Server was assessed with vulnerabilities (e.g. SSL Certificate Signed Using Weak Hashing Algorithm); 3) VPE System needs feature enhancements; 4) No technical support for the old VPE system; 5) CPH64 hardware is candidate for decommissioning (8.5 years old); and 6) Database requires migration to a new VPE system/server.
References:
| Link: | https://learn.microsoft.com/en-us/lifecycle/announcements/windows-server-2012-r2-end-of-support
Change Request Category:
Hardware Requirement: | n/a
Software Requirement: | Database software (e.g. Postgres, SQL, etc.); Virtualized server (VM) for the New VPE System.
*NOTE: Target implementation date may vary depending on the IT Project planning after approval
• EVALUATION -- To be accomplished by the I.T. Change EVALUATOR
Evaluator's Name: | Andrew R. Ignacio |  |  |  |  | Date Evaluated: |  | October 10, 2023
Change Request Type:
NOTE: All I.T. Changes categorized as STANDARD Change are exempted in the I.T. Change Management Process.
Proceed with the Change Request: |  | In case of NO, what would be the Technical IMPACT OF NOT CHANGING:
Back-out Plan:
Utilize the old Excel-based Vendor Performance Evaluation system for manual proceesing, until such time that the New VPE System is ready. Else, use the virtualized (VM) old VPE System.
Analysis and Recommendation: | This IT Change request falls under the Normal category as defined in ISP-CP-7516 (Information Technology Change Management). Since risks were assessed, this should be authorized and therefore it should be scheduled to follow the complete IT change management process according to a standardized procedure.
• REVIEW -- To be accomplished by the I.T. Change LEAD and the I.T. Security MANAGER
I.T. Change Lead's Name: | Arnel R. Valondo | [5 empty] | Date Reviewed: |  | October 11, 2023
Operation Impact: | Affected Users:
| Downtime (e.g. 4 hours): |  |  | n/a
Initial Decision:
I.T. Security Manager's Name: | Delfin DG Jose, Jr. | [5 empty] | Date Reviewed: |  | October 16, 2023
Security Risk: (Ref.: ISP-CP-6101 Risk Management)
| Justification: |  |  | Low impact due to migration from Physical to Virtual machine.
Initial Decision:
• ASSESSMENT and CONCLUSION -- To be accomplished by the I.T. Change MANAGER
Overall Impact Level: | (Except for STANDARD Change)
| If MAJOR impact level, decision of I.T. Strategic Committee is required. | [6 empty] | Ref. MOM No.:
Date Concluded: |  |  |  |  | Final Decision:
Final Justification:
Way Forward:
Important Notes: |  |  |  |  | Approver's Name and Signature: |  |  | Demetrio P. Selga
RFC Approval Date: (n/a if disapproved)
Acknowledgment Signatures
Others (specify):
Standard
Approved
Disapproved
ATTACHMENT (HARD/SOFT-COPY)
ONLINE REFERENCE (Provide Link below)
NEW IMPLEMENTATION
ENHANCEMENT
DECOMMISSIONING
Emergency
Yes
No
Low
Medium
High
Critical
Proceed as planned
Do not execute
Consider alternatives
Normal
Approved
Disapproved
Approved
Disapproved
Minor
Major
N/A (Not Applicable)
Others (specify):
Revert to the last good known configuration
INITIATOR:
Date:
EVALUATOR:
Date:
I.T. SECURITY MANAGER:
Date:
PROJECT LEAD:
Date:
Company-wide
Group
Departmental
User (specify estimated number of users):
Division-wide
Center-wide

## CRCR Form (For Approved RFC)
CRCR No.: | CRCR-ICT-202Y-XXX |  | Change Request Completion Report |  | IT Change Lead:
Rev. No.: | 0 |  |  |  | Signature:
• Request For CHANGE Details
RFC Number: |  | RFC-ICT-202Y-XXX |  | RFC Approval Date: |  | 0
Project Title:
Project Duration: |  |  |  | Completion Date:
Project Description:
Issues Encountered & Back-out Plan Details
Summary / Conclusion
Note: provide link to next Sheet or attached supplemental documents for SUMMARY that requires comprehensive explanation
• Deliverables & Test Reports
Document Type |  | Document Name |  |  |  | Completion Date
Note: Internal Test Reports and/or Third Party (Vendor) reports shall be listed here
• User Acceptance / Acknowledgement by CHANGE Management Team
Change Management Role |  |  | Name |  | Signature / Date
IT Change Initiator(s)
Other User / Discipline Representatives
IT Security Manager
IT Change Manager
Note:This Completion Report shall serve as proof for the Change closure and acceptance from above signatories.