## VPE SYSTEM
Vendor Performance Evaluations System
(October 2023)
ITEM NO. | WORK ITEM |  | Plan | Actual | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March
[5 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1 | System Requirement/Setting and Configuration |  | 15% | 10%
| 1.1 | Kick-off meeting
| 1.2 | Initial gathering of User Requirements
| 1.3 | Meeting with Product Owner for Detailed Requirements
| 1.4 | Configuring new Virtual server
| 1.5 | Database Evaluation/Creation of fallback
| 1.6 | Setting up new DB on VM Server/Migration
2 | Development initialization (Design) |  | 15%
| 2.1 | Setup Development Environment
| 2.2 | Creation of Vendor information UI
| 2.3 | Evaluations UI
| 2.4 | Evaluation Types UI
3 | Model/View/Controller |  | 20%
| 3.1 | Creating Evaluations Model/View/Controller
| 3.2 | Creating UserList Model/View/Controller
| 3.3 | Creating UserList Model/View/Controller
| 3.4 | Creating Vendor List Model/View/Controller
| 3.5 | Setting up connections on new db and application Models
| 3.6 | Creation of Foreign Key relation, Evaluations <> Evaluation Criteria
| 3.7 | Creation of Foreign Key relation, Evaluations <> Evaluation Evaluation Type
| 3.8 | Creation of Foreign Key relation, Vendor <> Vendor Contact
| 3.9 | Creation of Foreign Key relation, Evaluation <> Vendor Details
4 | Additional Tables |  | 10%
| 4.1 | Setting up Approvers table on DB
| 4.2 | Setting up Checkers table on DB
5 | CRUD Operations |  | 10%
| 5.1 | Perform CRUD Operations on Evaluations model
| 5.2 | Perform CRUD Operations on EvaluationTypes model
| 5.3 | Perform CRUD Operations on User List model
| 5.4 | Perform CRUD Operations on Vendor model
6 | Validations |  | 10%
| 6.1 | Setting up server side/client side validation on Evaluations
| 6.2 | Setting up server side/client side validation on Vendor List
| 6.3 | Setting up server side/client side validation on Vendor Contacts
| 6.7 | Setting up server side/client side validation on Evaluation Criteria/Evaluation Type
7 | Authentication and Troubleshooting |  | 10%
| 7.1 | Log in Authentication set up
| 7.2 | Creation of excel/pdf output
| 7.3 | Troubleshooting/Debugging phase
8 | Maintenance and Adjustments |  | 10%
| 8.1 | Testing for overall performance
| 8.2 | Deployment to VM IIS server using wsgi
| 8.3 | Incase of delay * Set up old VPE Application to VM Server
| 8.4 | Evaluation of applications performance/operations
| 8.5 | User Acceptance Testing
TOTAL |  |  | 100% | 10%

## MH
October - December | 60
1hr/day | 20hrs/month
January - March | 120
2hrs/day | 40hrs/month
180MH